## Cover Page
Project Title: | Case Management Work Items
Prepared By: | Darla Poling
Details: | These are the work items for the epics I was assigned for the case management project. I decomposed the epics into features, then the features into user stories, and the user stories into tasks. This was uploaded into Azure DevOps as a bulk import of work items.
Notes: | This was a retrospective project based on a real-world implementation of a tech solution. I was only assigned 4/10 epics. The epics that weren't assigned to me include Public Portal Search & Indexing, Communication, Records Workflow, Online Portal View & Notifications, Security Access Control, Case Lifecycle Management, and Public Portal Submissions.

## Work Items
Title 1 | Title 2 | Title 3 | Title 4 | Work Item Type | Description | Acceptance Criteria | State | Tags
Compliance Division Workflow |  |  |  | Epic | Support the complete Compliance case workflow. |  | New | ProjectTag
| Case Review |  |  | Feature | Allow Compliance staff to review assigned cases and supporting documentation. |  | New | ProjectTag
|  | FR-012 View Assigned Cases |  | User Story | As Compliance staff, I want to view my assigned cases so that I can begin reviewing and managing them. | Given I am logged in as Compliance staff and have assigned cases; When I open the Case Review page; Then I shall see all cases assigned to me. | New | ProjectTag
|  |  | Configure Case Review Grid & Assignment Sync | Task | Configure Case Review grid filtered by assigned Compliance staff member, apply role-based access ( Compliance staff members see only their own cases), and set up trigger to sync the grid when a new case is assigned | Grid displays correct case set per logged-in Compliance staff member; RBAC verified (cross-staff isolation confirmed); workflow sync confirmed on a test assignment; empty state validated with zero assigned cases | New | ProjectTag
|  | FR-013 Review Supporting Documents |  | User Story | As Compliance staff, I want to review supporting documents so that I can make informed decisions on a case. | Given a case contains supporting documents; When I select a document from the case record; Then the document shall open for review. | New | ProjectTag
|  |  | Configure Supporting Document Viewer | Task | Configure document viewer/link within the case record to open supporting documents | Authorized user can open each supporting document from the case record; access respects document permissions; validated with at least one document per case type | New | ProjectTag
| Scheduling Hearings |  |  | Feature | Allow Compliance staff to schedule and manage hearings. |  | New | ProjectTag
|  | FR-020 Schedule Hearing |  | User Story | As Compliance staff, I want to schedule hearings so that cases can proceed through the hearing process. | Given a case is eligible for a hearing; When I schedule the hearing; Then the hearing date, time, and associated case shall be saved. | New | ProjectTag
|  |  | Configure Hearing Scheduling Form | Task | Configure hearing scheduling form (date, time, associated case) and persistence | Hearing date/time saved and correctly associated to the case; validated with a test case | New | ProjectTag
|  | FR-020 Modify Hearing Schedule |  | User Story | As Compliance staff, I want to modify scheduled hearings so that scheduling conflicts or changes can be accommodated. | Given a hearing has already been scheduled; When I update the hearing details; Then the revised schedule shall be saved and displayed. | New | ProjectTag
|  |  | Configure Hearing Schedule Edit | Task | Configure edit capability on an existing hearing schedule | Updated schedule saves and displays correctly; validated against a previously scheduled hearing | New | ProjectTag
| Assigning Cases |  |  | Feature | Allow Compliance staff members to assign cases to different Compliances. |  | New | ProjectTag
|  | FR-020 Assign Cases |  | User Story | As a Hearing Head, I want to assign a case to a Compliance staff member so that the case can go through it's full lifecycle. | Given that I am Compliance staff member and there is an open, unassigned case; When I select Assign Case and an Compliance staff member; Then the case is assigned to that Compliance staff member. | New | ProjectTag
|  |  | Configure Case Assignment Action | Task | Configure case assignment action (Compliance Head assigns an Compliance staff member) and trigger downstream sync to the Case Review grid | Assignment persists correctly and triggers the FR-012 grid update; validated with an open, unassigned test case | New | ProjectTag
| Draft Orders |  |  | Feature | Allow Compliance staff to create and manage draft orders. |  | New | ProjectTag
|  | FR-021 Create Draft Order |  | User Story | As Compliance staff, I want to create draft orders as PDF documents so that I can prepare proposed decisions for review. | Given I have an assigned case; When I create a draft order; Then the draft shall be saved as a PDF associated with the case. | New | ProjectTag
|  |  | Configure Draft Order Creation | Task | Configure draft order creation as a PDF, linked to the case record | Draft order PDF generated and saved to the case; validated with a sample case | New | ProjectTag
|  | FR-021 Edit Draft Order |  | User Story | As Compliance staff, I want to edit draft orders so that I can revise decisions before publication. | Given a draft order exists; When I make changes and save the document; Then the updated draft shall replace the previous version while preserving the document record. | New | ProjectTag
|  |  | Configure Draft Order Edit & Versioning | Task | Configure edit/versioning of an existing draft order | Edited draft replaces the prior version while preserving document history; validated against a test draft | New | ProjectTag
| Publish Orders |  |  | Feature | Allow Compliance staff to publish finalized orders. |  | New | ProjectTag
|  | FR-022 Publish Final Order |  | User Story | As Compliance staff, I want to publish finalized orders so that official case decisions become available. | Given a draft order has been finalized; When I publish the order; Then the order shall be marked as the official decision for the case. | New | ProjectTag
|  |  | Configure Order Publish Action | Task | Configure publish action marking a finalized order as the official case decision | Published order flagged as official; case decision reflects new status; validated with a finalized test draft | New | ProjectTag
|  | FR-022 Notify Stakeholders |  | User Story | As Compliance staff, I want stakeholders notified after an order is published so that all parties are aware of the decision. | Given an order has been published; When the publication is complete; Then the system shall generate the appropriate notifications according to system configuration. | New | ProjectTag
|  |  | Configure Stakeholder Notification Workflow | Task | Configure workflow to send notifications to stakeholders when an order is published | Notification generated and delivered per configuration upon publish; validated with test recipients | New | ProjectTag
| Close & Archive Cases |  |  | Feature | Allow Compliance staff to close completed cases and archive case records. |  | New | ProjectTag
|  | FR-023 Close Case |  | User Story | As Compliance staff, I want to close completed cases so that they are no longer available for active processing. | Given all required case activities have been completed; When I close the case; Then the case status shall be updated to Closed. | New | ProjectTag
|  |  | Configure Case Closure Action | Task | Configure case closure action that updates case status to Closed | Case status updates to Closed only when required activities are complete; validated with a completed test case | New | ProjectTag
|  | FR-023 Archive Case Records |  | User Story | As Compliance staff, I want completed case records archived so that they are retained for future reference and compliance. | Given a case has been closed; When the archive process is initiated; Then the case record shall be archived and remain available according to the retention policy. | New | ProjectTag
|  |  | Configure Case Archive Workflow | Task | Configure archive workflow retaining closed case records per the retention policy | Closed case is archived and remains retrievable per retention rules; validated with a closed test case | New | ProjectTag
System Performance |  |  |  | Epic | Ensure the application is performant, reliable, secure, and accessible. |  | New | ProjectTag
| Performance & Responsiveness |  |  | Feature | Maintain acceptable system performance and response times. |  | New | ProjectTag
|  | NFR-001 Load Pages Efficiently |  | User Story | As an attorney, I want public search results returned quickly so that I can efficiently locate case information. | Given I submit a valid public search; When the search is executed under normal load; Then the results shall be returned within 3 seconds. | New | ProjectTag
|  |  | Tune Public Search Performance | Task | Configure/tune public search query performance against the 3-second target | Search results return within 3 seconds under normal load in test environment | New | ProjectTag
|  | NFR-003 Load Public Portal Pages |  | User Story | As an attorney, I want public portal pages to load quickly so that I can efficiently complete my work. | Given I navigate to a public portal page under normal load; When the page loads; Then it shall load within 2 seconds. | New | ProjectTag
|  |  | Tune Public Portal Page Load Performance | Task | Configure/tune public portal page load performance against the 2-second target | Public portal pages load within 2 seconds under normal load in test environment | New | ProjectTag
|  | NFR-002 Concurrent Staff Usage |  | User Story | As Records division staff member, I want to be able to use the system when 99 other people are using it without performance degredation, so that I can complete my work regardless of how busy the system is. | Given that 99 other internal staff users are using the system; When I use the system as a fellow internal staff member; Then the performance of the system will remain the same. | New | ProjectTag
|  |  | Load Test Concurrent Staff Usage | Task | Load-test the system with 100 concurrent internal staff sessions and tune configuration as needed | No performance degradation observed with 100 concurrent staff sessions in test environment | New | ProjectTag
|  | NFR-017 Concurrent Public Usage |  | User Story | As an attorney, I want to be able to use the system when 99 other people are using it without performance degredation, so that I can complete my work regardless of how busy the system is. | Given that 99 other public users are using the system; When I use the system as a fellow public user; Then the performance of the system will remain the same. | New | ProjectTag
|  |  | Load Test Concurrent Public Usage | Task | Load-test the system with 100 concurrent public sessions and tune configuration as needed | No performance degradation observed with 100 concurrent public sessions in test environment | New | ProjectTag
| Availability & Reliability |  |  | Feature | Maintain reliable system availability and recoverability. |  | New | ProjectTag
|  | NFR-013 Maintain System Availability |  | User Story | As an attorney, I want the system available during business hours so that I can complete my work without interruption. | Given it is between 7:00 AM and 6:00 PM MT Monday through Friday; When I access the system; Then the system shall be available 99.5% of the time. | New | ProjectTag
|  |  | Configure Availability Monitoring | Task | Configure uptime monitoring/alerting against the 99.5% business-hours availability target | Monitoring confirms the availability target is met over a representative monitoring period | New | ProjectTag
|  | NFR-014 Perform Daily Backups |  | User Story | As Records staff, I want the system backed up daily so that case information can be recovered if needed. | Given the scheduled backup time occurs; When the backup process begins; Then the system shall successfully perform a daily backup. | New | ProjectTag
|  |  | Configure Automated Daily Backup Workflow | Task | Configure scheduled workflow for automated daily backups | Backup runs successfully on schedule; restoration verified from at least one backup | New | ProjectTag
|  | NFR-015 Recover From Outages |  | User Story | As an attorney, I want the system restored after an outage so that I can resume work with minimal disruption. | Given an unplanned outage occurs; When recovery procedures are initiated; Then the system should recover within 4 hours. | New | ProjectTag
|  |  | Configure & Document Outage Recovery Procedure | Task | Configure/document recovery procedure targeting a 4-hour RTO | Simulated outage recovery completed within 4 hours in test; procedure documented | New | ProjectTag
| User Experience & Accessibility |  |  | Feature | Provide an accessible and user-friendly experience across supported platforms. |  | New | ProjectTag
|  | NFR-009 Meet Accessibility Standards |  | User Story | As an attorney, I want the application to comply with accessibility standards so that I can effectively use the system regardless of ability. | Given I access the public portal; When I interact with the application; Then it shall comply with WCAG 2.1 Level AA standards. | New | ProjectTag
|  |  | Validate WCAG 2.1 AA Accessibility | Task | Configure/validate public portal pages against WCAG 2.1 Level AA standards | Accessibility audit/scan shows no Level AA violations on public-facing pages | New | ProjectTag
|  | NFR-010 Support Modern Browsers |  | User Story | As an attorney, I want the application to work in supported browsers so that I can access the system regardless of my browser choice. | Given I access the application using Chrome, Edge, Firefox, or Safari; When I use one of the two most recent browser versions; Then the application shall function correctly. | New | ProjectTag
|  |  | Validate Cross-Browser Support | Task | Validate application functionality on the two most recent versions of Chrome, Edge, Firefox, and Safari | Core functionality confirmed working on all four browsers, two most recent versions each | New | ProjectTag
|  | NFR-011 Flexible User Interface |  | User Story | As an attorney, I want an intuitive interface so that I can efficiently perform my daily tasks regardless of my technical proficiency. | Given that I am a professional of low or moderate computer skills, when I use the system, then I quickly find what I need. | New | ProjectTag
|  |  | Review UI Usability Across Proficiency Levels | Task | Configure/review the UI for usability across varying levels of technical proficiency | Usability walkthrough confirms key tasks are completable without specialized training | New | ProjectTag
|  | NFR-012 Mobile Responsive Design |  | User Story | As an attorney, I want the application to display properly on mobile devices so that I can access information while away from my workstation. | Given that I am accessing the system from a mobile device; When I interact with the application; Then it shall function just as well. | New | ProjectTag
|  |  | Configure Mobile Responsive Layout | Task | Configure responsive layout for mobile devices | Application displays and functions correctly on representative mobile screen sizes | New | ProjectTag
| Administrative Control |  |  | Feature | Provide administrative capabilities for system management. |  | New | ProjectTag
|  | NFR-020 Configure System Settings |  | User Story | As Records staff, I want to configure system settings without code deployment so that configuration changes can be made efficiently. | Given I have administrative privileges; When I modify a supported system configuration; Then the change shall take effect without requiring code deployment. | New | ProjectTag
|  |  | Configure No-Code Settings Panel | Task | Configure an administrative settings panel for no-code configuration changes | A configuration change is applied and takes effect without a code deployment; validated with a test change | New | ProjectTag
|  | NFR-021 Manage User Roles |  | User Story | As Records staff, I want administrative interfaces for managing user roles so that I can efficiently administer user access. | Given that I am a staff of the Records division; When I change a user's roles; Then the user has a different set of permissions. | New | ProjectTag
|  |  | Configure Role & Permission Admin Interface | Task | Configure administrative interface for managing user roles and permissions | Admin can update a user's role and permission changes take effect immediately; validated with a test account | New | ProjectTag
| Compliance & Security |  |  | Feature | Protect system data and ensure compliance with security requirements. |  | New | ProjectTag
|  | NFR-004 Encrypt Confidential Documents |  | User Story | As Records staff, I want confidential documents encrypted so that sensitive information remains protected while stored. | Given a confidential document is stored; When it is saved to the repository; Then it shall be encrypted using AES-256 or equivalent. | New | ProjectTag
|  |  | Configure Document Encryption at Rest | Task | Configure AES-256 (or equivalent) encryption at rest for confidential documents | Confidential document confirmed encrypted in storage; validated via storage inspection | New | ProjectTag
|  | NFR-005 Secure Data Transmission |  | User Story | As an attorney, I want my data transmitted securely so that confidential information cannot be intercepted. | Given data is transmitted between the user and the system; When communication occurs; Then HTTPS/TLS 1.2 or higher shall be used. | New | ProjectTag
|  |  | Configure TLS/HTTPS Enforcement | Task | Configure HTTPS/TLS 1.2+ enforcement across all endpoints | All data transmission confirmed over TLS 1.2+; validated via security scan | New | ProjectTag
|  | NFR-019 Record Administrative Actions |  | User Story | As Records staff, I want administrative actions logged so that system activity can be audited. | Given a Records staff member performs an administrative action; When the action is completed; Then the system shall record the user ID, timestamp, and action details. | New | ProjectTag
|  |  | Configure Admin Action Logging | Task | Configure logging of administrative actions (user ID, timestamp, action) | An admin action produces a complete audit log entry; validated with a test action | New | ProjectTag
Document Management |  |  |  | Epic | Manage the storage, retrieval, organization, and security of case documents. |  | New | ProjectTag
| PDF Annotation |  |  | Feature | Allow users to annotate PDF documents. |  | New | ProjectTag
|  | FR-024 Add PDF Annotations |  | User Story | As an attorney, I want to annotate PDF documents so that I can record comments and observations during case review. | Given I have an authorized PDF document open; When I add comments or highlights; Then the annotations shall be saved with the document. | New | ProjectTag
|  |  | Configure PDF Annotation Tools | Task | Configure PDF annotation tools (comments, highlights) within the document viewer | Authorized user can add comments/highlights to an open PDF; validated with a test document | New | ProjectTag
|  | FR-024 Save PDF Annotations |  | User Story | As an attorney, I want my PDF annotations saved so that my review notes are retained. | Given annotations have been added; When I save the document; Then the annotations shall persist with the PDF. | New | ProjectTag
|  |  | Configure Annotation Persistence | Task | Configure persistence of annotations with the source document | Annotations persist and reload correctly after save/reopen; validated with a test document | New | ProjectTag
| Confidential Documents |  |  | Feature | Protect confidential documents from unauthorized access. |  | New | ProjectTag
|  | BR-003 Restrict Document Access |  | User Story | As Legal & Utilities staff, I want confidential documents restricted to authorized users so that sensitive case information remains protected. | Given a document is marked confidential; When an unauthorized user attempts to access it; Then access shall be denied. | New | ProjectTag
|  |  | Configure Confidential Document Access Restriction | Task | Configure access restriction on documents marked confidential | Unauthorized user denied access to a confidential document; validated with a test account | New | ProjectTag
|  | BR-002 Log Confidential Document Access |  | User Story | As Records staff, I want access to confidential documents logged so that document access can be audited. | Given an authorized user accesses a confidential document; When the document is opened; Then the access shall be recorded in the audit trail. | New | ProjectTag
|  |  | Configure Confidential Access Logging | Task | Configure audit logging specifically for confidential document access events | Access to a confidential document produces an audit trail entry; validated with a test access | New | ProjectTag
| Upload Documents |  |  | Feature | Allow users to upload case documents. |  | New | ProjectTag
|  | FR-004 Upload Documents |  | User Story | As an attorney, I want to upload documents so that supporting materials are associated with my filing. | Given I am creating a filing; When I upload a supported PDF document; Then the upload shall complete successfully. | New | ProjectTag
|  |  | Configure PDF Upload at Filing | Task | Configure PDF upload capability at time of filing | Supported PDF uploads successfully and associates with the filing; validated with a test upload | New | ProjectTag
|  | FR-010 Validate Uploaded Documents |  | User Story | As Records staff, I want uploaded documents validated so that incomplete or invalid filings are rejected before acceptance. | Given a document is uploaded during filing; When required information or formatting is invalid (Document # = DOC-#########-YR [with alphabetic suffixes for related documents ie 001, 001A, 001B], Docket # = YR-#####-DEP); Then the filing shall be rejected and validation errors displayed. | New | ProjectTag
|  |  | Configure Filing Validation Rules | Task | Configure validation rules for uploaded documents, including document/docket number formats (DOC-#########-YR, YR-#####-DEP) | Invalid filings (missing fields, malformed document/docket numbers) rejected with clear validation errors; valid filings accepted; validated per filing type (telecom, utilities, pipeline) | New | ProjectTag
| View & Download Documents |  |  | Feature | Allow users to view and download authorized documents. |  | New | ProjectTag
|  | FR-013 View Documents |  | User Story | As an attorney, I want to be able to view documents so that I can conduct research for cases. | Given that I am an attorney; When I select View Document; Then the document will be displayed on the screen. | New | ProjectTag
|  |  | Downloader UI | Task | Build document downloader UI. | Click to view action on documents with confidentiality checks where necessary. | New | ProjectTag
|  | FR-013 Download Documents |  | User Story | As an attorney, I want to download authorized documents so that I can review them offline. | Given I have permission to access a document; When I select Download; Then the document shall be downloaded successfully. | New | ProjectTag
|  |  | Configure Document Download | Task | Configure document download capability for authorized users | Authorized user successfully downloads a document; validated with a test document | New | ProjectTag
|  | Preserve Document Integrity |  | User Story | As an attorney, I want downloaded documents to remain unchanged so that the downloaded copy accurately reflects the stored document. | Given that I have permission to download a document; When I download that document; Then the resolution and content will align exactly with the stored version. | New | ProjectTag
|  |  | Configure Download Integrity Check | Task | Configure checksum/hash verification to ensure the downloaded document matches the stored version | Downloaded document content/resolution confirmed identical to the stored version; validated with a test document | New | ProjectTag
| Document Versioning |  |  | Feature | Maintain document version history. |  | New | ProjectTag
|  | Create New Document Version |  | User Story | As an attorney, I want document revisions saved as new versions so that previous versions are preserved. | Given that I I have permission to edit a document; When I make an edit or revision to a document; Then the revisions will be saved as a new version to preserve version history. | New | ProjectTag
|  |  | Configure Document Version Creation | Task | Configure version creation on document edit/revision | Edited document saves as a new version while preserving prior versions; validated with a test edit | New | ProjectTag
|  | View Version History |  | User Story | As an attorney, I want to view previous document versions so that I can review changes over time. | Given that I have persmission to view a document; When I select View Versions history; Then the document's version history will be displayed for me. | New | ProjectTag
|  |  | Configure Version History View | Task | Configure version history view for documents | Authorized user can view full version history for a document; validated with a multi-version test document | New | ProjectTag
User Registration & Account Management |  |  |  | Epic | Manage user registration, authentication, account access, and account security. |  | New | ProjectTag
| Sign-Up Page |  |  | Feature | Allow public users to register and access the system. |  | New | ProjectTag
|  | FR-025 Register Tier 1 Account |  | User Story | As a public citizen, I want to register a Tier 1 account so that I can access available public portal features. | Given I am an unregistered user; When I submit valid registration information; Then the system shall create a Tier 1 account. | New | ProjectTag
|  |  | Configure Tier 1 Registration Form | Task | Configure Tier 1 public registration form and account creation | Valid registration creates a Tier 1 account; validated with a test submission | New | ProjectTag
|  | FR-001 Authenticate Account |  | User Story | As an attorney, I want to authenticate my account so that I can securely access the system. | Given I have a registered account; When I enter valid login credentials; Then I shall be granted access to the system. | New | ProjectTag
|  |  | Configure Login/Authentication Flow | Task | Configure login/authentication flow | Valid credentials grant access; invalid credentials denied; validated with test accounts | New | ProjectTag
| Account Verification |  |  | Feature | Verify newly registered user accounts. |  | New | ProjectTag
|  | FR-001 Verify Account |  | User Story | As an attorney, I want my account verified so that I can securely access system features. | Given I have completed registration; When my account verification is successful; Then my account shall become active. | New | ProjectTag
|  |  | Configure Account Verification Step | Task | Configure account verification (activation) step after registration | Account becomes active only after successful verification; validated with a test registration | New | ProjectTag
|  | FR-049 Noficiation of Account Verification |  | User Story | As a tier 1 user, I want a notification of account verification so that I can know my account has been successfully created and verified. | Given I have completed registration; When my account verification is successful; Then I will receive an e-mail notification. | New | ProjectTag
|  |  | Configure Verification Email Notification Workflow | Task | Configure workflow to send an email notification upon successful verification | Verified user receives an email notification; validated with a test account | New | ProjectTag
| Profile Creation |  |  | Feature | Manage user profile information required for account access. |  | New | ProjectTag
|  | FR-001 Create Profile |  | User Story | As a tier 1 user, I want the ysstem to create an account so that I can access the functionalities of the system. | Given I have completed registration: When my account has been verified; Then the system will create a unique tier 1 account for me. | New | ProjectTag
|  |  | Configure Automatic Profile Creation | Task | Configure automatic profile/account creation upon successful verification | Unique Tier 1 account created and accessible after verification; validated with a test registration | New | ProjectTag
| Tier 2 Upgrade |  |  | Feature | Allow Tier 1 users to request Tier 2 access. |  | New | ProjectTag
|  | FR-048 Apply for Tier 2 Upgrade |  | User Story | As a Tier 1 user, I want to apply for Tier 2 access so that I can submit new filings through the public portal. | Given I have a Tier 1 account; When I submit a Tier 2 upgrade request; Then my request shall be submitted for review. | New | ProjectTag
|  |  | Configure Tier 2 Upgrade Request | Task | Configure Tier 2 upgrade request submission for Tier 1 users | Submitted upgrade request routed for review; validated with a test account | New | ProjectTag
|  | FR-048 Review Tier 2 Upgrade |  | User Story | As Records staff, I want to review Tier 2 upgrade requests so that eligible users receive the appropriate level of access. | Given a Tier 2 upgrade request has been submitted; When I approve or deny the request; Then the system shall record the decision and update the user's account accordingly. | New | ProjectTag
|  |  | Configure Tier 2 Upgrade Review Workflow | Task | Configure Records staff review/approval workflow for Tier 2 upgrade requests | Approval or denial updates the requesting user's account accordingly; validated with a test request | New | ProjectTag